# REQUEST FOR PROPOSAL — Commercial Due Diligence

Kestrel Ridge Partners · Project Paws · Issued 26 July 2026

## 1. About the sponsor

Kestrel Ridge Partners is a lower-middle-market private equity firm ($650M AUM) investing in healthcare and consumer services in the United States.

## 2. The opportunity

We are in exclusivity on a group of 42 veterinary clinics across the US Southeast, approximately $120M revenue. The business is founder-owned and has been built by acquiring independent practices one at a time over eight years.

## 3. Objective

An independent commercial view to support our Investment Committee on 21 August 2026.

## 4. Scope — questions to answer

| # | Question |
| --- | --- |
| Q1 Market | Is pet-care spending still growing, or was the pandemic surge a one-off? |
| Q2 Retention | How loyal are pet owners when a practice changes hands and the veterinarian they knew leaves? |
| Q3 Competition | What is the threat from the large consolidated chains and corporate owners? |
| Q4 Runway | Is there still runway to acquire independent practices at the prices being paid today? |
| Q5 Thesis | A view on the seller’s stated 6–8% organic growth. |

## 5. Information available to the adviser

- Financials by clinic, three years

- Anonymised client list

- Seller’s information memorandum

No customer or client interviews have been conducted to date.

## 6. Deliverables

- 20–25 page deck, IC-ready

- Supporting model

- Verbal readout to the deal team

## 7. Timeline

| Milestone | Date |
| --- | --- |
| Proposal due | Wednesday 29 July 2026 |
| Work start | Monday 3 August |
| Draft readout | 18 August |
| Investment Committee | 21 August |

## 8. Indicative budget

$55,000–75,000.

## 9. What the proposal should contain

Approach and workplan · team and relevant experience · what you need from us · assumptions and risks · fees and terms.

## 10. Contact

Dana Whitfield, Partner — d.whitfield@kestrelridge.com