## Slide 1: Project Paws — commercial due diligence
29 July 2026
Proposal to Kestrel Ridge Partners · Investment Committee, 21 August 2026 · Private and confidential

## Slide 2: Two of your five questions decide this deal — retention and the 6-8% claim — and neither can be answered from the data room alone
THE READ
1
Q2 and Q5 are the two that decide this deal
Market growth, the corporate threat and acquisition runway shape the price of 42 clinics. Retention after a founder leaves, and the 6-8% claim, decide whether there is a deal at all.
2
The data room alone cannot answer them
Financials, a client list and the memorandum establish what happened, not why. No customer interview has been conducted, so a loyalty read built on revenue trends is correlation sold as cause.
3
Your own record is the test bed
8 years of one-at-a-time deals give a staggered series of founder exits. Read against the client file, attrition becomes measurable; 30 owner interviews then establish why.
4
One senior, 14 working days, $75,000 fixed
The same person frames, analyses and presents, with a draft readout on 18 August. If owner access is refused the engagement is $58,000 for a data-room-only read on Q2.
Source: Kestrel Ridge Partners RfP, 26 July 2026. Fee and workplan as proposed.

## Slide 3: Sector growth is price-led, not volume-led, so the seller's 6-8% claim cannot be read against a rising market — it has to be decomposed
THE READ — Q1 AND Q5
US VETERINARY PRACTICE REVENUE GROWTH DECOMPOSITION, 2024-2025, %
+6.6
Service price
-1.2
Volume and mix
+5.4
Revenue growth
→ The growth on offer is priced growth — so the seller's 6-8% has to be decomposed before it can be believed
WHAT THE SECTOR DATA ESTABLISHES
• Prices rose 6.6% in 2024-25 while revenue rose 5.4% — the gap is volume and mix, and it is negative.
• Visits fell 3.5%, 1.4%, 2.6% and 3.1% across 2022-2025 — four straight years of decline.
• Category spend still grew to $41bn in 2025: the market expands on price, not on visits.
WHAT IT MEANS FOR THE SELLER'S CLAIM
• A 6-8% organic claim needs pricing above market or volume against a falling tide.
• Both series are sector-level; we test whether they share a perimeter before leaning on the gap.
• We bridge same-store growth into price, volume, mix and acquired revenue, clinic by clinic.
Sources: Vetsource 2026 pricing data reported by Provet; Vetsource visit white paper, January 2026 vintage; APPA 2026.

## Slide 4: Eight years of one-at-a-time deals give a staggered series of founder exits — we read them as a cohort, then ask owners why
APPROACH — Q2
ANSWERING Q2 — YOUR OWN RECORD, THEN THE OWNERS
From the data room
From the field
Into the model
Client list
12m attrition
Cause split
30 owners
6 ex-vets
Risk bands
→ You get a banded retention risk you can price — not a causal claim the evidence cannot carry
WHAT YOUR OWN RECORD CAN SETTLE
• 42 acquisitions, less those inside 12 months and those with a system migration, give the events.
• Each exit is read 12 months either side, against clinics where the founder stayed.
• We size both arms on day 3; on a plausible split the usable cohort is 12-16 events.
WHAT OWNERS SETTLE, AND WHAT STAYS UNCERTAIN
• 30 interviews across 4 Southeast markets say whether the vet, the price or the wait drove it.
• 6 conversations with departed vets on why clients followed them, or did not.
• The output is a banded retention risk, not causal proof: price resets travel with exits.
Source: RfP section 5. Identification rests on exits staggered across the eight years, and on data sufficiency.

## Slide 5: Retention runs from day one and carries no float — the other four workstreams are sequenced behind it
APPROACH — WORKPLAN
WORKPLAN, 3-20 AUGUST 2026 (14 WORKING DAYS), COMMITTEE 21 AUGUST
Aug 3-7
Aug 10-14
Aug 17-20
IC Aug 21
WS1 Market
Price/vol
Region
WS2 Retention
Cohort
Interviews
Synthesis
WS3 Chains
Catchment
WS4 Runway
Density
WS5 Thesis
Bridge
Readout
IC pack
→ Retention is the only workstream with no float — so the client list and the interview ruling are what we need on day one, not in week two
WHAT WE NEED IN THE FIRST 48 HOURS
• Data room access 3 August, financials by clinic and the memorandum in native format.
• Client list with clinic identifier, visit dates, and the clients who have lapsed.
• Vet roster with dates, total practices ever acquired, and your ruling on owner outreach.
WHAT GOVERNS THE PACE
• Retention starts day one: interview recruitment, not analysis, is the constraint.
• Q3 maps chain clinics, pricing and hours per catchment; Q4, independents and prices paid.
• We deliver the Committee pack on 20 August; say if your pre-read needs it earlier.
Source: RfP sections 4 and 7. Q3 reads catchment overlap with corporate chains; Q4, independent density and prices paid.

## Slide 6: Five assumptions carry this workplan. The client list is the one that can break it, so each carries its own fallback
TERMS — ASSUMPTIONS AND RISKS
Assumption
Why it matters here
If it does not hold
The client list carries a clinic identifier, visit dates and lapsed clients
The cohort is built from client-level behaviour, and the owners who left are the ones the retention question turns on.
We fall back to a revenue-based attrition estimate and say plainly that it is weaker. Raised on 3 August, not discovered on 18 August.
At least 10 founder exits have 12 clean months either side, with no system migration
Too few exits means too few events, and a migration destroys the history the design reads. Where the founder left at close, exit and acquisition cannot be separated, so those events are read apart.
We publish the funnel on day 3 and say plainly that the read has become directional, before any finding rests on it.
We may approach pet owners in the group's own markets
The causal read on Q2 comes from owners explaining their decision. The floor is 24 owner interviews; below it the finding is directional only.
The engagement becomes $58,000 for a data-room-only read on Q2, and we tell your Committee that read is weaker.
No management access beyond the data room, 0 hours assumed
The work is priced on that basis. Two hours with the founder would materially tighten the view on the 6-8% claim, and we recommend you seek it.
If access is granted we use it and tell you what changed. No fee adjustment either way.
14 working days, scope as set out on slides 4 and 5
The Committee date is fixed and the schedule holds only 2 days of float, after the 18 August readout.
A change in scope, or a data dependency arriving after 5 August, moves the readout day for day. We say so the same day.
→ Every one of these is checkable in the first 48 hours, which is when we would rather find out than on 18 August
Assumptions stated as at 29 July 2026, on the basis of the RfP and without data room access.

## Slide 7: One senior frames, analyses and presents. You are buying the person who will be in the room on 21 August, not a pyramid
TERMS — TEAM
Who does the work
[REPLACE BEFORE SENDING - your name], former Engagement Manager at a top-tier strategy firm, now independent. 1 senior, 0 handovers between the model and your Committee on 21 August.
Why that matters on this timetable
14 working days leave no room for a handover between an analyst who found the pattern and a partner who explains it. Senior-only delivery is a schedule decision as much as a quality one.
Relevant experience
[REPLACE BEFORE SENDING - two or three comparable engagements with year and scope, for example a commercial due diligence on a multi-site healthcare roll-up. Anonymised references are accepted.]
What you are not buying
No bench, no standing research team, no proprietary owner panel. That is the concentration risk you take, and this proposal does not pretend to cover it: 36 interviews is what one senior can recruit and run in 14 days.
→ Senior-only delivery is what makes 14 working days feasible. It is also the concentration risk you take, and we do not pretend otherwise
Team as proposed for Project Paws. Client references available on request.

## Slide 8: $75,000 fixed — 14 days of senior time and 36 interviews run personally, $58,000 if owner access is refused
TERMS — FEES
FEES AND TERMS — PROJECT PAWS, AUGUST 2026
$75,000
FIXED FEE
Expenses included
36
INTERVIEWS
30 owners, 6 ex-vets
14
DAYS
3-20 Aug, senior only
50/50
PAYMENT
On start, on delivery
Project Paws · 42 clinics · Investment Committee 21 August 2026
→ The constraint is recruiting 30 owners, not calling them — below 30 we say so the day it is clear
WHAT THE FEE COVERS
• 36 interviews run personally, the clinic-level model, a 20-25 page IC deck and the readout.
• $75,000 is 14 days of senior time at one rate, expenses included — the top of your range.
• No success fee, no contingent element. If owner access is refused: $58,000, data room only.
TERMS
• Half on start, half on delivery of the IC pack. Valid 30 days from submission.
• Liability capped at fees paid. For Kestrel Ridge only, no third-party reliance.
• Mutual confidentiality, IP on payment. No engagement with the seller, target or a bidder.
Owner data held pseudonymised and encrypted, destroyed on completion apart from our working papers. Fees in USD.