## Slide 1: Project Paws — commercial due diligence
3 August 2026
Mandate KRP-DD-2026-014 · Confidential — subject to NDA

## Slide 2: Ninety minutes, one binding outcome — a named owner and a committed date against every P1 data-room item
AGENDA
1
Mandate read-back · 8 min
Confirm the five questions of KRP-DD-2026-014 are still the five questions, and surface any drift now rather than on 18 August.
2
Workplan and dependencies · 12 min
WP1 complete; WP3 and WP4 start this afternoon on public data; WP2 waits on two dates; WP5 assembles all four into the bridge.
3
WP1 first read, both sides · 15 min
The market does not supply 6–8% organic growth — and the case that cuts the other way, stated at its strongest.
4
Data-room request, line by line · 25 min
The P1 band walked item by item, with a named owner and a committed date against each one. This is the meeting.
5
The seven open hypotheses · 10 min
What we will attempt to disprove between now and 18 August — and what the deal team already suspects but has not written down.
6
Voice-of-customer · 10 min
No pet owner has been interviewed and none will be invented; the interview programme, and the access decision it needs today.
7
Timeline, risks, decisions · 10 min
The 11 August checkpoint, the two risks to the critical path, and the four decisions to be closed before we leave the room.
Source: mandate KRP-DD-2026-014, RFP issued 26 July 2026.

## Slide 3: Eleven working days separate work start from the draft readout — which puts the data room, not the analysis, on the critical path
THE CLOCK
ENGAGEMENT SCHEDULE, 3–21 AUGUST 2026
Late July
3–7 Aug
10–14 Aug
17–21 Aug
WP1 Market — complete
WP3 Competition
WP4 Runway
WP2 Retention — partial
WP5 Thesis and bridge
Draft → IC
5 Aug P1 due
11 Aug check
→ Every day the P1 items slip comes out of WP2 — the one work package that cannot be compressed.
WHAT THE SCHEDULE IS REALLY CONSTRAINED BY
• WP1 is complete; WP3 and WP4 start 3 August, all on public data the seller does not control.
• WP2 needs close and vet-departure dates; three years of annual financials cannot supply them.
• WP5 assembles the bridge from all four and is not defensible before 14 August.
THE TWO DATES TO FIX IN THIS MEETING
• 5 August for the P1 band — the only date that keeps a measured attrition figure in scope.
• 11 August for the checkpoint — the last point at which the work can be redirected.
• Past 8 August WP2 becomes a caveat, and the Committee underwrites the seller's assumption.
Source: RFP timeline, mandate KRP-DD-2026-014 (work start 3 August · draft readout 18 August · Investment Committee 21 August).

## Slide 4: WP1 is complete and two more work packages start this afternoon; the fourth needs two dates the mandate pack did not deliver
THE WORKPLAN
THE FIVE WORK PACKAGES, BY DEPENDENCY
Five work packages
42 clinics · $120m
1
Runs on public data
WP1 Market — complete
WP3 Competition
WP4 Runway — 3 Aug
→ Not in the seller's gift
2
Partly blocked
WP2 Retention
Have: 3yr financials
Need: close/vet dates
→ Two dates unlock it
3
Consumes the other four
WP5 Thesis bridge
Not before 14 August
Carries the verdict
→ Capped by the last input
→ Sequencing is fixed by dependency, not preference — which is why the data room decides the shape of the readout.
WHAT EACH GROUP CAN AND CANNOT DO TODAY
• WP1, WP3 and WP4 answer market, competition and runway from public filings and reporting.
• WP2 holds three years of annual clinic financials but not the close and vet-departure dates.
• WP5 is the assembly of the other four, so it is capped by the last input to arrive.
WHY THIS SHAPE MATTERS TO THE COMMITTEE
• Three of the five mandate questions rest on evidence the seller cannot shape or withhold.
• The fourth is what the valuation rests on, and two dates from the seller unblock it.
• A measured figure or a stated range — which of the two is decided here, not by analysis.
Source: mandate KRP-DD-2026-014, questions Q1 to Q5; engagement methodologies WP1 to WP5 and the dependency note.

## Slide 5: US veterinary spending rose 40% in nominal terms since 2019 but, deflated by its own price index, the market is 5% smaller than before the pandemic
WP1 — MARKET
US VETERINARY SPEND BY YEAR, INDEX 2019 = 100
Nominal
Real
’19
100
100
0
’21
108.3
117.1
-8.8
’22
104.2
122.5
-18.3
’23
101.6
130.8
-29.2
’24
98.3
135.8
-37.5
’25
95.1
139.9
-44.8
Change
100
120
140
index, 2019 = 100
→ The nominal series says growth and the deflated series says contraction — the Committee must be told which one it is buying.
WHAT THE TWO SERIES SAY
• Nominal spend rose +39.9%, from $29.3bn in 2019 to $41.0bn in 2025 — the memorandum's series.
• Prices rose 47% over the same six years, so real spend is −4.9% against 2019 and falling.
• 2020 is left blank, not interpolated: no citable APPA figure exists for that year.
WHY THIS IS THE FIRST SLIDE OF THE MARKET CASE
• Underwriting 6–8% growth in a contracting market means underwriting further price rises.
• The deflator cuts both ways: a services-only index overstates the fall, leakage understates it.
• It must be re-derived on the target's own clinic revenue — which the P1 band unblocks.
Source: APPA veterinary spend (current USD) deflated by BLS CPI veterinarian services, 2019 = 100. 2020 left blank; 2023 derived (Probable).

## Slide 6: WP1 settles one hypothesis of the eight and reopens two the first read closed too early, including the labour question
WP1 — VERDICTS
H1 — GROWTH IS PRICE, NOT VOLUME. CONFIRMED.
In 2025 veterinary service prices rose 6.5% while clinical visits fell 3.1%, leaving practice revenue up roughly 2.5%. Two volume sources built on entirely different collection methods agree on direction: Vetsource's transactional feed from 6,451 US practices, and IDEXX's same-store clinical visits at −1.9%. They differ by about 60% on magnitude, which is carried as a sensitivity.
H2 — VOLUMES FELL; THE CAUSE IS NOT SETTLED.
Our first read called the cohort mechanism refuted on the strength of a record dog population. That tested the wrong thing: the mechanism is age mix, not population level. A 2020–21 puppy consumes a heavy first-year schedule and far fewer visits thereafter, which produces the observed decline while the population rises. Affordability produces the same curve. Public data cannot separate them — item P1-f can.
H3 — VETERINARIAN SUPPLY: CONTESTED.
Brakke Consulting, for the AVMA, finds graduates from existing colleges likely sufficient to 2035 — but new schools add only about 4% of veterinarians by then, so relief lands after the hold period. Mars Veterinary Health claims a 55,000 shortfall by 2030, on a method Brakke rebuts. Both are national. Neither tests these catchments, which is what item P3-d exists to do.
THE OTHER SIDE OF THE CASE
A contracting real market is an entry-price tailwind: seller expectations follow the nominal series. Consolidators took share from under 10% to roughly 25% of clinics while the real market shrank. If Mars is right on supply, this platform's assembled clinician base is itself the scarce asset. And six years of 6.5–9.4% price rises taken and held is evidence of pricing power, not only of strain.
→ Two of the three are corrections to our own first read — better made in this room than at the Committee on 21 August.
Source: BLS CPI veterinarian services; Vetsource, 6,451 US practices; IDEXX FY2025; Brakke Consulting for the AVMA; Mars Veterinary Health. WP1 note v5.

## Slide 7: Seven hypotheses remain open, and the one the deal turns on needs two dates that the mandate pack did not carry
WHAT REMAINS OPEN
1
H2 · Why visit volumes are falling — cohort ageing or affordability
WP1, reopened. Both mechanisms produce the same curve; one resolves on a demographic clock, the other worsens with price. Item P1-f separates them.
2
H3 · Whether veterinarian supply binds in these catchments
WP1/WP3, contested nationally. Brakke and Mars disagree, and neither is Southeast-specific. Item P3-d is the only local test.
3
H4 · Loyalty attaches to the veterinarian, not the premises
WP2, blocked. The one the deal turns on: it needs close dates and vet-departure dates against the clinic cohort.
4
H5 · Consolidation has concentrated in metropolitan catchments
WP3, from 3 August. If it holds, a platform weighted to smaller catchments faces a different threat from the headline figure.
5
H6 · Entry multiples have risen, compressing the arbitrage
WP4, from 3 August. Decides whether the buy-and-build engine still pays for itself, or whether the spread is already competed away.
6
H7 · Runway is set by the filters, not the raw count of independents
WP4, from 3 August. Catchment fit, a revenue floor, owner succession and consolidator presence decide what is acquirable.
7
H8 · 6–8% organic does not survive once the drags are subtracted
WP5. The market supplies ~2.5% nominal, so the claim needs the platform to beat it by 350–550bps a year while volumes contract.
→ Four can be settled on public data; three need the seller, and one of those three decides the deal.
Source: WP1 note v5 §2; engagement methodologies WP2, WP3, WP4, WP5. H2 to H8 are open hypotheses, not findings.

## Slide 8: Six P1 items decide whether the Committee is handed a measured attrition figure or an honest range, and two of them are simply dates
DATA ROOM
P1 item requested
Unblocks
If it does not arrive
Close date and founding-vet departure date, per acquired practice
WP2 — separates the ownership change from the vet departure
H4, the deal's central open hypothesis, cannot be tested at all
Active clients AND visits by clinic, monthly, back to 2019
WP2 cohort event study; WP1 decomposition on the platform itself
No attrition measurement, and no way to place the target against the market's own shape
Revenue by clinic, monthly, back to 2019 (annual will do for earlier years)
WP2 revenue retention; WP5 same-store growth
Same-store growth cannot be verified and the 6–8% claim stays untestable
Vet retention status at close, for each of the 42 clinics
WP2 value at risk on the unlocked clinics
Exposure can only be shown on the platform average, which understates it
P1-e · Reconciliation of the $120m revenue base, by clinic and service line
WP1 and WP5 — explains ~$2.9m per clinic against a $1.5m AVMA average
The Committee sees a revenue base at 1.8–1.9× the benchmark with no stated reason
P1-f · Visit frequency by pet-age cohort, from the practice-management system
WP1 and WP5 — separates cohort ageing from affordability
H2 reaches the Committee unresolved, and the growth bridge carries an unexplained drag
→ A request that states its own consequence gets returned faster than one that does not — hence the third column.
Source: engagement methodology WP2 (cohort, event study, value at risk); WP1 note §9. Target figures come from the data room, never an estimate.

## Slide 9: No pet owner has been interviewed, so the deck carries a named programme of 6 interview groups — 2 of which need no access from the seller
INTERVIEWS
Founding vets of two earlier tuck-ins
They have already lived the transition being underwritten. Settles whether clients followed them, and over what period. Access through Dana or the seller.
Practice managers at three clinics
They see churn before it reaches the numbers. Settles what clients actually say when they leave. Requires management access.
Two associate vets who stayed
The succession case is the mitigation being relied on. Settles what made staying viable after the founder left. Requires management access.
One regional referral specialist
Sees case flow across several practices at once. Settles where volume goes when a practice changes hands. Needs no permission from the seller.
Eight to ten pet owners, three catchments
Split lapsed and active. Settles whether these clinics lose visits to price, to a competitor, or to a specific veterinarian's departure.
Two software or buying-group executives
Gives a Southeast benchmark against the national Vetsource and IDEXX series. Settles whether the region tracks the national visit decline. No permission needed.
→ Two of the six need no permission from the seller, so the programme survives a refusal of decision D2.
Source: RFP §5 (no customer interviews conducted to date); engagement methodology WP2 interview programme; WP1 note §10 additions.

## Slide 10: Four decisions close in this room today, and two risks are named now so that neither of them arrives as a surprise on 21 August
DECISIONS
A ACCOUNTABLE · R RESPONSIBLE · C CONSULTED · I INFORMED
Dana Whitfield
Deal team
Adviser
D1 · Data-room owner and committed dates
D2 · Access to management and founding vets
D3 · Written basis of the 6–8% claim
D4 · Mid-point checkpoint, 11 August
A
R
C
A
I
C
I
A
C
A
I
R
→ Three of the four decisions are Dana's alone — which is why they are put to her in the room and not in a follow-up email.
WHAT EACH DECISION COSTS IF IT IS DEFERRED
• D1 deferred: WP2 slips, and the Committee gets a range where it expected a measured figure.
• D2 deferred: the interview programme stays a recommendation instead of becoming evidence.
• D3 and D4 deferred: the bridge tests an interpreted claim, with no chance to redirect.
THE TWO RISKS, NAMED AND MITIGATED
• R1, data-room slippage past 8 August — committed dates today, escalation to Dana at 48 hours.
• R2, scope creep — any addition after 11 August is an explicit trade against a named item.
• Named now rather than reported later: a risk raised at the readout is heard as an excuse.
Source: mandate KRP-DD-2026-014; engagement methodologies WP2 and WP5; notes/KOM-briefing-note-v3.md §7 and §10.

## Slide 11: Five dates carry this engagement, and only the first two are still inside this room's control
NEXT STEPS
1
3 August · Kick-off
Scope confirmed against the five mandate questions, decisions D1 to D4 closed in the room, and a named owner with a committed date against every P1 item.
2
5 August · P1 band due
Clients, visits and revenue by clinic back to 2019, close and veterinarian-departure dates, and the reconciliation of the $120m revenue base.
3
11 August · Mid-point check
Emerging findings with Dana, hypotheses standing or refuted, and the last point at which the work can still be redirected before the draft is written.
4
18 August · Draft readout
Verbal readout to the deal team: the organic growth bridge, the sensitivity that decides it, and the draft verdict with its conditions attached.
5
21 August · Investment Committee
Proceed, dig deeper or pass — stated plainly, with the conditions attached and the single assumption that would break the thesis named.
→ The first two dates are the only ones this meeting can still move; the last three are fixed by the Committee calendar.
Source: RFP timeline, mandate KRP-DD-2026-014; engagement dependency note. Checkpoint date subject to decision D4.

## Slide 12: Thank you — questions
Jean-Christophe Lanoix
COMMERCIAL DUE DILIGENCE · KRP-DD-2026-014 · CONFIDENTIAL
jcl@turboconsultant.com