# REQUEST FOR PROPOSAL — EV Charging: Strategic Options

Verdal Group · Issued 15 July 2026

## 1. About us

Verdal Group operates 1,100 supermarkets across six European countries. Most sites have large customer car parks.

## 2. Background

Customers increasingly expect charging at our stores. Today we lease parking space to two charging operators under long-term agreements and earn a nominal fee. The Board believes we are leaving value on the table and has asked management to assess bringing charging in-house.

A Board paper circulated in June states that the European EV charging market will be worth €25bn by 2030. We would like this figure tested before any commitment is made.

## 3. Objective

An independent, defensible view of whether Verdal should operate charging itself — and if so, where and how.

## 4. Scope — work packages

| # | Work package |
| --- | --- |
| WP1 Market | Size the opportunity genuinely addressable by Verdal. Test the €25bn Board figure. |
| WP2 Segment | Fast, ultra-fast or destination charging — which fits our footprint and our customer dwell time? |
| WP3 Geography | Which of our six countries first, and why. |
| WP4 Competition | Who operates today, and what economics do they actually achieve. |
| WP5 Entry mode | Build, buy or partner — with candidate profiles and a recommendation. |
| WP6 Plan | A 100-day plan for the recommended route. |

## 5. Information available to the adviser

- Store list by country, with car park capacity

- Current lease terms with both charging operators

- Energy procurement contracts (summary)

No customer research has been conducted.

## 6. Deliverables

- Board-ready deck

- Excel model, assumptions visible and editable

- One-page recommendation

## 7. Timeline

| Milestone | Date |
| --- | --- |
| Proposal due | 29 July 2026 |
| Kick-off | 4 August |
| Interim review | 8 September |
| Final delivery | 30 September 2026 |

## 8. Evaluation

Quality of reasoning and transparency of assumptions will weigh more than volume of output. We will favour advisers who tell us where the data is weak.

## 9. Contact

Katrin Sommer, VP Strategy — k.sommer@verdalgroup.eu