## Slide 1: EV charging: strategic options
29 July 2026
Request for Proposal of 15 July 2026 · Confidential

## Slide 2: Three sections: what has to be settled first, how the six work packages answer it, and what it costs
CONTENTS
1
01 · The question behind the question
What has to be settled before the opportunity can be sized: which perimeter the Board figure sits on, how a number Verdal can act on is built, and where the deciding evidence actually lives
2
02 · The six work packages
Method and deliverable for each of WP1 to WP6, and the reasoning behind each methodological choice
3
03 · How it runs, and what it costs
The six material evidence gaps and who closes each, the eight-week schedule, who is bidding and what happens if they stop, and the offer with its options

## Slide 3: The question behind the question
01
What has to be settled before the opportunity can be sized

## Slide 4: The €25bn cannot carry this decision as it stands — it does not say what it counts, and fixing that perimeter is where the work starts
THE QUESTION
1
Situation
1,100 stores, large car parks, two long-term charging leases at a nominal fee. The Board believes value is being left on the table and wants an independent view on bringing charging in-house.
2
Complication
The EUR 25bn cannot carry a capital decision as it stands. Published forecasts of the European charging market measure different things, and no European grocer has ever disclosed what charging actually earns. There is no benchmark to borrow.
3
What we propose
Six work packages, one senior, EUR 80,000, delivered 30 September: a Board-ready deck, an Excel model with every assumption visible and editable, and a one-page recommendation.
Source: Verdal Group Request for Proposal, 15 July 2026.

## Slide 5: Published forecasts of the European charging market do not count the same things — most include home charging, which no retailer can serve
THE QUESTION — PERIMETER
WHAT EACH PUBLISHED FORECAST INCLUDES, BY PERIMETER
Hard-
ware
Soft-
ware
Install.
Public
charging
Home /
work
Forecast A
Forecast B
Estimate 2018
Public pool
WHY THIS COMES FIRST
• Each house publishes against its own definition, unstated.
• Residential is the swing: none of it is open to a retailer.
• Two houses, same claimed scope, materially different totals.
WHAT WP1 DOES ABOUT IT
• We establish which perimeter the Board figure sits on.
• Then rebuild it on the perimeter Verdal can act on.
• This sizes the prize; it does not challenge the instinct.
Source: scope statements as published by each research house; our review, July 2026. Perimeters shown as published.

## Slide 6: A number Verdal can act on sits five deductions below any European total, and each deduction is a separate analysis with its own evidence
THE QUESTION — SIZING
FROM A EUROPEAN TOTAL TO A VERDAL-ADDRESSABLE FIGURE
EU market
1 · Private
Home charging
2 · Energy
Not margin
3 · Segments
En-route
4 · Your six
Unnamed in RfP
5 · Share
Incumbents
→ Each layer is arguable on its own evidence, so the Board can move one assumption and see the consequence rather than accept a single aggregate
THE DISCIPLINE THIS IMPOSES
• Each layer is a separate analysis with its own evidence.
• Revenue is not margin — the layer most often skipped.
• Layer four needs the six named. One question at kick-off.
WHAT YOU GET FROM IT
• A number the Board can interrogate layer by layer.
• An explicit statement of which layer carries most doubt.
• A second build; disagreement is reported, not averaged.
Source: our decomposition method. Magnitudes are the output of WP1, not an input to this proposal.

## Slide 7: Six of eight European grocers publish what they built; none of the eight publishes what it earns
THE QUESTION — EVIDENCE
CHARGING DISCLOSURE BY EUROPEAN GROCER, JULY 2026
Grocer
Points
Tariff
Use
Economics
Sainsbury's, UK
Lidl/Schwarz, DE
Aldi Sud, DE
Carrefour, FR
Mercadona, ES
Colruyt, BE
Tesco, UK
Delhaize, BE
→ The build is public and the returns are not, across all eight — so no peer number can be borrowed and the business case has to be measured
WHAT THE PATTERN SHOWS
• The left of this grid is public; the right is empty.
• Even the owned networks report milestones, never economics.
• Where a partner is listed, its accounts can be read instead.
WHAT IT MEANS FOR THIS WORK
• No peer number can be borrowed. The case must be measured.
• An adviser claiming a benchmark has pure-play or vendor data.
• Every claim carries verified, probable or hypothesis.
Source: annual reports, press releases and national charge point registries; our review, July 2026.

## Slide 8: The evidence that decides this case is not in the market — it is in your car parks, your till data and your two lease contracts
THE QUESTION — YOUR DATA
Source you own
What it yields
How we obtain it
When it lands
Your car parks
Time parked against time in store; bay turnover by format and daypart
Direct observation at six to ten sites across three countries
Weeks 2 to 4
Your till and loyalty data
Basket of charging customers against matched controls; visit frequency before and after installation
Difference-in-differences on your own anonymised extracts
Phase 2, October to November
Your two lease contracts
Metered throughput per point; session distribution, uptime, arrival state of charge
Requested from both lessees under the existing reporting terms
Day 1, at no cost
→ No competitor bidding for this work can reach any of these three; you can reach all three, and one at Day 1 for nothing
Source: our gap analysis against the six work packages, July 2026.

## Slide 9: Revenue per bay is sessions times energy times margin — and one of those three terms has never been measured at a grocery site
THE QUESTION — SEGMENT
REVENUE PER BAY PER YEAR, ITS THREE TERMS
Revenue per bay
Sessions per day
Time parked
not measured
Session duration
Energy per session
Curve at real SoC
Sharing, winter
Margin per kWh
Network tariff
Energy procurement
WHERE THE ARITHMETIC BREAKS
• Published dwell measures time in store, not time parked.
• That gap sets the denominator for energy and bay turnover.
• Arrivals are mid-charge, so delivered power is below nameplate.
HOW WE CLOSE IT
• Module M1 measures time parked at 6-10 of your sites.
• Curves modelled at real arrival SoC, sharing, winter derating.
• Output: bay yield by power class, with tipping points named.
Source: published charging curve measurement and retail dwell research; our decomposition, July 2026.

## Slide 10: Six work packages under one governing question: what carries this decision if the charging margin does not
THE QUESTION — SCOPE
GOVERNING QUESTION MAPPED TO THE SIX WORK PACKAGES
Operate charging itself?
What can we
address?
What do operators
achieve?
What is the
route in?
WP1 Market
WP2 Segment
WP3 Geography
WP4 Competition
WP5 Entry mode
WP6 100-day plan
→ The six work packages are not six studies but three questions, which is why the answer arrives as one recommendation rather than six annexes
WHY THE QUESTION READS THIS WAY
• The Board's premise is that value is being left on the table.
• Grocers who in-housed priced below market: control, not margin.
• So the study answers both readings, not the charging line alone.
HOW THE SCOPE MAPS
• WP1 to WP3 answer what Verdal can genuinely address.
• WP4 is the reality check on what those three produce.
• WP5 and WP6 turn the answer into a route in and a plan.
Source: Verdal Group Request for Proposal, section 4; our structuring.

## Slide 11: The six work packages
02
Method and what each one produces

## Slide 12: WP1 builds the market number twice, by two independent routes — so the Board sees where they agree, and where they do not
WP1 MARKET
Step
What we do
What it puts in your hands
Perimeter test
Establish what each published forecast actually counts — hardware, services, home charging — and which perimeter the Board figure sits on
A written reconciliation of the EUR 25bn: what it measures, and what it does not
Rebuild the funnel
Build the number bottom-up from the vehicle parc: energy demand, the share that passes a public point, realised price
A market model with every assumption visible and editable by your own team
Deduction ladder
Strip out, layer by layer, what Verdal cannot serve — private charging, energy pass-through, en-route and kerbside, the countries you are not in
The addressable figure, each layer carrying its own evidence and confidence level
Independent cross-check
Build the same number a second time from bay throughput upward, and reconcile the two
Either two routes that agree, or a disagreement reported rather than averaged away
Sensitivity
Move each assumption across its plausible range and see which ones change the recommendation
The shortlist of assumptions actually worth arguing about at Board level
→ Two routes to one number, reconciled in the open — a single build can be argued with, two that agree cannot
Source: our method. Magnitudes are the output of WP1, not an input to this proposal.

## Slide 13: WP2 makes the segment choice follow delivered energy, not nameplate power — five market assumptions replaced by five measurements
WP2 SEGMENT
SEGMENT INPUTS: ASSUMPTION AGAINST MEASURED BASIS
Market assumes
Nameplate power
Published dwell time
Vendor basket claims
22 kW as default
One product estate-wide
We measure
Delivered energy at real arrival SoC
Time parked at your sites
Basket on your till data
Power class against your dwell
Segment by store format
WHY NAMEPLATE MISLEADS HERE
• Shoppers arrive part-charged; batteries accept less then.
• Shared dispensers halve output exactly at peak trading hours.
• Pre-conditioning is navigation-linked; a local trip misses it.
WHAT WP2 PRODUCES
• Delivered energy by power class against real parking windows.
• Bay yield per year by format, not one estate-wide average.
• The tipping points that would change the power class.
Source: published charging curve measurement; our method design, July 2026.

## Slide 14: WP3 screens the six countries on grid access and tariff structure, not on EV penetration — four lanes, sixteen checks each
WP3 GEOGRAPHY
COUNTRY SCREENING FRAMEWORK, FOUR LANES
Demand
Grid
Tariff
Rules
Parc
Home
Public
Catchment
Lead time
Threshold
Steps
Queue
Charged?
Low use
Relief
Curve
Mandates
Status
Car parks
Capex
WHY PENETRATION IS THE WRONG SCREEN
• The highest EV share can sit with the longest queue.
• Whether capacity is charged matters more than the energy price.
• Connection cost moves in steps; a threshold decides the spec.
WHAT THE SCREEN PRODUCES
• A per-country cost curve for the same physical installation.
• Where building is becoming obligation rather than choice.
• A lead market, a follower, and what would reorder them.
Source: our screening design, July 2026. Country findings are the output of WP3.

## Slide 15: WP4 reads achieved economics from audited disclosure and your incumbents' own meters, not from operator claims
WP4 COMPETITION
COMPETITION EVIDENCE CHAIN, FIVE SOURCES
A confidence level on every claim
Contradictions reported, not smoothed
Audited
disclosure
National
registries
Your lessees'
meters
Peer
interviews
Counterparty
review
Margin
→ Achieved economics sit in audited accounts and in your lessees' meters; operator claims are the one source we do not treat as evidence
WHERE THE REAL NUMBERS ARE
• Listed operators publish audited utilisation, price and cost.
• National registries settle the inconsistent retailer counts.
• Your two lessees hold the most relevant dataset in Europe.
WHY COUNTERPARTY REVIEW MATTERS
• A large retail charging partner lost almost all its equity.
• A lease moves capex off the balance sheet, not the risk.
• We read both lessees' accounts, break rights and end-of-term.
Source: our method design for WP4, July 2026.

## Slide 16: WP5 tests four routes on one set of criteria — and repricing what you already hold is carried as the fourth
WP5 ENTRY MODE
THE FOUR ENTRY MODES AGAINST THE CRITERIA WP5 TESTS
Entry mode
Capital
light
Control
gained
Speed to
first bay
Reversible
Build
Buy
Partner
Reprice
→ Repricing what you hold is the lightest and most reversible route, which is why it is carried until the model rules it out
WHY A FOURTH OPTION BELONGS
• The RfP asks build, buy or partner. The grievance is a fee.
• A lease fee can be renegotiated without a capital programme.
• Testing it costs little and guards against over-solving.
HOW THE OPTIONS ARE TESTED
• One model, four routes, same assumptions and downside case.
• Candidate profiles, so a decision can be acted on.
• Conditions precedent and kill criteria attached to the answer.
Source: RfP scope, section 4; option space and criteria ours. Positions illustrative, not a finding.

## Slide 17: WP6 builds the 100-day plan backwards from the first irreversible commitment, and names what must be true before you reach it
WP6 100-DAY PLAN
INDICATIVE 100-DAY PLAN, THREE HORIZONS
Days 1-30
Days 31-60
Days 61-90
Secure grid access rights
Property
Open tender or renegotiation
Procurement
Stand up the baseline
Data
Site selection on bay yield
Property
Counterparty and term sheet
Legal
Pilot specification
Operations
Pilot commitment
COMEX
Capability decision
HR
Gate review
Board
→ Sequencing is set by the pilot commitment — everything before it is arranged to make that decision as informed and as reversible as it can be
WHY IT IS BUILT BACKWARDS
• The pilot commitment is the first spend that cannot be undone.
• Grid access is a queue; position in it is not recoverable later.
• The baseline starts early, so there is a before to read against.
WHAT COMES WITH THE PLAN
• Named owners mapped onto functions Verdal already has.
• A risk register with kill criteria: stopping is a planned outcome.
• A capability decision point: hire, contract or partner.
Source: our plan design, July 2026. Actions indicative and refined against the WP5 recommendation.

## Slide 18: How it runs, and what it costs
03
Gaps, timetable, who is bidding, and the offer

## Slide 19: Four of the six material gaps close on data you already own — the one that moves the answer most closes on none
DELIVERY — GAPS
SIX EVIDENCE GAPS BY EFFECT, CLOSABILITY AND ROUTE
Evidence gap
Effect
Yours
Route
Metered throughput
Day 1
Arrival SoC
Day 1
Time parked
M1
Concession terms
M2
Peer economics
Audited
Basket uplift
Ph. 2
→ Two gaps close at Day 1 under contracts you already hold; the one that moves the answer most closes on no budget by desk research
NAMING THE WEAK DATA, AS ASKED
• The basket effect moves the answer most, on the least evidence.
• Circulating figures differ from the causal study by two orders.
• Closing it by literature review is overselling. It needs your data.
WHERE THE WORK STARTS
• Four close in weeks from data you or your lessees meter.
• Two need money and access, and are priced separately.
• What we cannot close is reported unclosed, with its confidence.
Source: our gap analysis against the six work packages, July 2026.

## Slide 20: The interim review carries the market and segment answer, so September is spent on the decision rather than on catching up
DELIVERY — SCHEDULE
ENGAGEMENT SCHEDULE, EIGHT WEEKS, THREE MILESTONES
W1
W2
W3
W4
W5
W6
W7
W8
WP0 Mobilise
WP1 Market
WP2 Segment
WP3 Geography
WP4 Competition
WP5 Entry mode
WP6 Plan
Deliverables
Kick-off 4 Aug
Interim 8 Sep
HOW THE WEEKS ARE SEQUENCED
• Market and segment are front-loaded, settled before the interim.
• Competition overlaps, because it depends on external access.
• Entry mode and the plan take the final four weeks.
WHAT YOU SEE, AND WHEN
• Weekly check-ins: what moved, what is stuck, what we need.
• 8 September: market and segment answers, assumptions exposed.
• 30 September: Board deck, editable model, one-page recommendation.
Source: Verdal RfP section 7 for milestone dates; scheduling ours.

## Slide 21: One senior carries this end to end, and the two things a Board asks about a sole adviser are answered here rather than left open
DELIVERY — WHO IS BIDDING
Where this comes from
Independent strategy and transformation practice, founded after eight years at a top-tier strategy firm, latterly as Engagement Manager. Work is executive-committee level: growth strategy, performance and cost, operating model, strategic due diligence for funds. The delivery standard is the one that firm applies — hypothesis-driven, fact-based, answer first — carried by one senior rather than a pyramid of juniors.
Comparable decisions taken to a board
[TO COMPLETE BEFORE SENDING] Three engagements: one capital-allocation decision of comparable size, one adjacent-market entry with a build-buy-partner recommendation, one commercial due diligence for a fund. For each: the question asked, the recommendation made, and what the client decided. Client names withheld pending release.
What happens if I am unavailable
A named associate of equivalent seniority is briefed at kick-off and holds read access to the working files throughout, so the engagement does not stop. If a delay is material, the fallback delivery date of 14 October is already worked out and the interim review on 8 September is unaffected. Professional indemnity cover is in place; evidence available on request.
Source: our own record. Client names withheld pending release.

## Slide 22: The base scope answers the RfP in full by 30 September; the two options add evidence no adviser can buy for you
THE OFFER
Base scope · EUR 80,000
All six work packages answered and delivered on your date, 30 September. A Board-ready deck, an Excel model with every assumption visible and editable by your team, and a one-page recommendation. The six material evidence gaps are named, ranked by how far each one would move the answer, with a costed plan for closing each. This is a complete, defensible answer to the question you asked.
Base + your own evidence · EUR 94,000
Adds the two measurements no adviser can buy on your behalf. A dwell study at six to ten of your sites establishes time parked against time in store — the input that sets bay economics and that nobody has measured at a grocery site. A structured tender to three operators reveals the commercial terms no retailer concession in Europe discloses, and prices what your existing leases are worth repriced. Needs two further weeks; we recommend 14 October rather than a thinner analysis.
Basket study, phase 2 · EUR 20,000
Settles the largest swing factor in the whole case on your own point-of-sale and loyalty data: does charging lift the basket, and by how much. The only causal study in the literature is from another continent and another sector mix, and every larger figure in circulation is vendor marketing. Verdal is one of very few parties in Europe able to measure this rather than cite it. Runs eight to twelve weeks from October — decided at the Board read-out, not before.
→ One senior from framing to Board read-out — the reader of your leases is the builder of the model and the person who presents it
Fees exclude VAT. Field cost for the dwell study is invoiced at the agency's own invoice, no mark-up. Payment 30% kick-off, 30% interim, 40% delivery.