## Slide 1: EV charging: strategic options
Verdal Group · 4 August 2026
Mandate VG-STRAT-2026-07 · prepared for Katrin Sommer, VP Strategy, and the Board

## Slide 2: This hour settles the method and the inputs, not the answer — and three of the six decisions cannot wait for the interim
KICK-OFF
1
The mandate, and how the six work packages divide it
Three start on 4 August on public evidence. Three wait on Verdal. The recommendation consumes all of them and cannot be brought forward.
2
How the Board figure will be tested — the method, not a result
Charging figures are quoted at four levels that differ by orders of magnitude. The test locates the figure on that chain. No reconstruction is presented today.
3
What this engagement can and cannot establish
Three things cannot be produced inside the timeline, and each is named here with the substitute that replaces it, rather than discovered in the final week.
4
What we need from Verdal, and by when
Twenty data-room items, of which six block analysis, all dated 11 August. Nineteen interviews, twelve of them inside Verdal.
5
Six decisions asked of this meeting — three of which cannot wait
The six countries in scope, the Board paper's citation, and a named owner against each blocking item. The other three can follow in the week.
→ Nothing in this deck is a result. The results land at the interim, on 8 September.
Source: RfP, Verdal Group, 15 July 2026, sections 3-4; mandate VG-STRAT-2026-07.

## Slide 3: The mandate
01

## Slide 4: One decision breaks into six work packages, and three of them start on public evidence while the other three wait on Verdal
THE MANDATE
1
WP1 · Market — size what Verdal can actually address, and test the Board figure
Perimeter discipline first, then a funnel down to the site-host level with every basis visible. Public data plus one client parameter.
2
WP2 · Segment — the power level the dwell time can absorb
kWh delivered equals power times dwell. Arithmetic settles this before strategy does. Needs the dwell distribution; a stated assumption until then.
3
WP3 · Geography — which of the six countries first, and why
Two axes built from measured components: country economics against right to win. Lease encumbrance is the sleeper and can outrank economics.
4
WP4 · Competition — what European operators actually achieve
Unit economics reconstructed from public disclosure, every undisclosed line marked and bounded. Utilisation is derived, never asserted.
5
WP5 · Entry mode — build, buy, partner, or renegotiate
Four options, not three: the current arrangement stays priced to the end. Scored against criteria agreed in advance, then tested against constraints.
6
WP6 · Plan — a hundred days ending in one numeric gate
Written for the recommended route only. It converts the largest unknown into a measured number, cheaply, before capital is committed.
→ Five of the six blocking data items sit on WP1 and WP3 — the packages that start first are not the ones that finish first.
Source: RfP, Verdal Group, 15 July 2026, sections 3-4; mandate VG-STRAT-2026-07.

## Slide 5: Three work packages start on 4 August on public data alone, which makes 11 August — not the analysis — the date that decides the quality of the answer
THE MANDATE
WORK-PACKAGE SEQUENCE, 4 AUGUST TO 30 SEPTEMBER 2026
4 Aug
11 Aug
25 Aug
8 Sep
22 Sep
WP1 Market — public data
WP3 Geography — public data
WP4 Competition — public data
WP2 Segment — needs dwell data
WP5 Entry mode — consumes WP1-4
WP6 Hundred-day plan
Today
→ The critical path runs through the data room, not the analysis.
WHAT THE SEQUENCE RESTS ON
• Three packages need no Verdal input: filings, registries, tariffs.
• WP2 waits on one parameter — the dwell-time distribution.
• WP6 is written for the recommended route only, then rewritten.
WHERE THE TIMETABLE IS FRAGILE
• Data after 11 August becomes a stated assumption, not a delay.
• Analysis closes 15 September so the deck can be built and audited.
• The interim carries direction and the fact base, not the answer.
Source: engagement methodologies 01-06, VG-STRAT-2026-07. No analytical result is presented at kick-off.

## Slide 6: How the figure will be tested
02

## Slide 7: Charging market figures are quoted at four levels that differ by orders of magnitude, and Verdal earns at the narrowest of them
HOW THE FIGURE WILL BE TESTED
THE FOUR LEVELS AT WHICH A CHARGING FIGURE IS QUOTED, NARROWEST FIRST
Site-host margin — Verdal
Operator revenue, gross
Energy value at the plug
Infrastructure capex
→ A figure sized at the widest level and applied at Verdal's overstates the prize.
WHAT SEPARATES ONE LEVEL FROM THE NEXT
• Capex is spent on charging, not earned from it.
• Energy value passes mostly through to the electricity supplier.
• Operator revenue is gross, before energy, hardware and grid.
WHY ONLY VERDAL'S LEVEL MATTERS HERE
• Verdal is a landowner: a fee, a share, or the operating margin.
• Each level is a fraction of the wider one beneath it here.
• That arithmetic is what WP1 exists to prevent getting wrong.
Source: engagement methodologies 01-06, VG-STRAT-2026-07. No analytical result is presented at kick-off.

## Slide 8: The figure is located rather than reproduced or dismissed — three steps, and three things the method deliberately will not do
HOW THE FIGURE WILL BE TESTED
1 · RECONSTRUCT — LOCATE EVERY CONSTRUCTION OF THIS ORDER
Find each published figure near this magnitude for Europe around 2030 and record, at source, exactly what it measures, its geography and its horizon. A number read through a secondary summary is not read at source, and the distinction decides whether the reconstruction holds.
2 · BUILD VERDAL'S OWN FUNNEL, BASIS BY BASIS
European public charging energy, then the destination-charging share, then the grocery share of destination charging, then the six countries, then Verdal's addressable share, then margin per kWh at the site-host level. Every step states its basis and its confidence level.
3 · PUT BOTH FIGURES ON ONE EXHIBIT
The Board's number and the Verdal-level number side by side, with the perimeter difference visible and the bridge between them drawn. That page is the deliverable of the work package; everything before it exists to make it defensible.
WHAT THE METHOD DELIBERATELY REFUSES TO DO
It does not re-forecast the European market — a fifth forecast added to four existing ones settles nothing. It does not start from the assumption that the Board figure is wrong. And it does not fill an undisclosed line with a plausible value: where a figure cannot be sourced, the deck says so and bounds it.
→ A refutation, if there is one, has to be earned from sources — it is not the starting hypothesis.
Source: engagement methodologies 01-06, VG-STRAT-2026-07. No analytical result is presented at kick-off.

## Slide 9: No published source has yet been found stating the claim in those terms, which is why the Board paper's own citation is the first item we ask for
HOW THE FIGURE WILL BE TESTED
Construction type
What it measures
Horizon and geography
Why it is not the confirmed source
A traceable primary source
The originating document behind the Board paper's figure, whatever it turns out to measure
Would match the claim exactly, by definition
Searched for and not found. Two independent passes of the published literature returned no source stating the claim in those terms. Requested as DR-01.
Cumulative build-out capex
What building the European charging network costs — money spent on charging, not earned from it, and earned by equipment makers and installers
Cumulative to 2030, Europe
A cumulative total is not an annual market, and the paper does not say which of the two it means. The two readings differ by roughly seven times.
Annual energy value at the plug
The whole electricity bill through European public charge points in a single year, before any cost is deducted
Annual 2030, Europe
Most of it is the cost of the electricity itself and passes to the supplier. The published range across sources is wide enough to bracket the claim from either side.
Equipment-market forecasts
Sales of charging hardware, installation and embedded software across the European market
Annual 2033 and 2034, Europe or EU-27
The horizon is not 2030, so the figure is not comparable as stated. Three of the closest digit matches carry horizons three or four years later.
→ None of these is ranked against the others. The paper's own citation is what would settle it.
Source: published market and industry literature reviewed to 27 July 2026. No figure is attributed to the Board paper, whose source has not been identified.

## Slide 10: What can and cannot be established
03

## Slide 11: Three things cannot be produced inside this mandate; each is named now, with the substitute that replaces it
WHAT CAN AND CANNOT BE ESTABLISHED
No voice of the customer
No customer research has been conducted, and none can be commissioned, analysed and defended before 30 September. Willingness to pay and charging behaviour will not be asserted. In its place: the interview programme, any EV data Verdal already holds against its loyalty base, and — decisively — a pilot measurement specified in the hundred-day plan.
No destination-charging utilisation benchmark
Every published European utilisation figure covers highway or mixed networks. The operators whose estates most resemble Verdal's disclose nothing, and utilisation is the single variable that decides profitability. In its place: the throughput data held by Verdal's two incumbent operators, and a bounded range with its derivation shown until that data arrives.
No confident continental benchmark for what a site host is paid
Lease fees and revenue shares in European retail charging deals are almost universally undisclosed, and what benchmark exists is single-market and contested between sources. In its place: Verdal's own two agreements read in full, and an anonymised read from a retail property adviser in each of the six countries.
→ None is fatal. Each converts into an interview, a client dataset or a pilot measurement.
Source: RfP section 5 (no customer research conducted); methodologies 01, 02 and 04.

## Slide 12: The engagement runs on four hypotheses, and every one of them is open today — the work is designed to close them, not to confirm them
WHAT CAN AND CANNOT BE ESTABLISHED
THE FOUR WORKING HYPOTHESES AND THE TEST THAT CLOSES EACH
Hypothesis
Verdict
Confidence
Planned tests
The Board figure measures a level of the chain above the one Verdal earns at
2 tests
Dwell time at a grocery store caps the power level that can pay for itself
2 tests
Utilisation, not price, decides whether operating charging is profitable
2 tests
Existing lease terms, not country economics, decide where Verdal could move first
2 tests
Open
Confidence, 1 to 5 filled pastilles
Confidence is a judgement drawn as pastilles, never a measured probability.
Tests that do not fit the row are COUNTED, never cut.
→ A hypothesis closed by argument rather than by its named test has not been closed.
WHY THE STATUS READS OPEN, FOUR TIMES
• Each is stated so that it can be refuted. Otherwise it is not one.
• Confidence is low on all four — the honest position at week zero.
• Every figure carries a label: verified, probable, or hypothesis.
HOW EACH ONE CLOSES
• The test is fixed now, not once the answer is visible.
• Where a test needs Verdal data, the request item is named.
• Where the evidence does not exist, the deck says so.
Source: engagement methodologies 01-06, VG-STRAT-2026-07. No analytical result is presented at kick-off.

## Slide 13: What we need from Verdal
04

## Slide 14: Twenty items are requested and six block analysis; the two that matter most together define what Verdal already earns
WHAT WE NEED FROM VERDAL
Ref
Item
Unblocks
Needed by
DR-01
The June Board paper, and the source citation behind the figure
WP1 — the figure test
11 August
DR-02
Both incumbent operator agreements, in full — not in summary
WP1, WP3, WP5 — exclusivity decides sequencing
11 August
DR-03
Store list by country, with tenure and lease expiry
WP1, WP3 — the denominator for every sizing
11 August
DR-04
Car park capacity, and the bays realistically convertible
WP1, WP2, WP3 — the most sensitive parameter
11 August
DR-06
Dwell-time distribution by store archetype — not the average
WP2 — the whole work package
11 August
DR-09
Charging income actually received, per site, last three years
WP1, WP5 — the counterfactual
11 August
→ Verdal's counterfactual is not zero — it is the current arrangement.
Source: data-room request list, mandate VG-STRAT-2026-07. Dates back-planned from final delivery on 30 September 2026.

## Slide 15: Four dates carry the engagement, and 11 August decides its quality — after it, the analysis runs on our assumptions rather than Verdal's data
WHAT WE NEED FROM VERDAL
Date
Milestone
What it has to produce
What it decides
4 August
Kick-off
Six decisions, of which three cannot wait: the six countries, the Board paper's citation, and a named owner against each blocking data item
Whether the engagement starts on Verdal's facts or on our assumptions
11 August
Blocking data due
The six items on the previous page, in full — the operator agreements read rather than summarised
Whether WP1, WP2 and WP3 report on client data or on stated assumptions
8 September
Interim review
WP1 to WP4 in draft: the sizing and the perimeter test, the segment arithmetic, the country screen, and what operators actually achieve
The direction of the recommendation, and whether any work package needs redirecting
30 September
Final delivery
Board deck, Excel model with visible and editable assumptions, one-page recommendation, data-room request list and interview programme
Whether Verdal commits capital, renegotiates, or waits — and on what conditions
→ An item that misses its date becomes a stated assumption, flagged where it is used.
Source: RfP, Verdal Group, 15 July 2026, sections 3-4; mandate VG-STRAT-2026-07.

## Slide 16: Six decisions are asked of this meeting, and the cheapest unblocks the most: which six countries are in scope
WHAT WE NEED FROM VERDAL
Confirm the six countries
The RfP says six European countries and stops. WP3 cannot rank a list it has not been given, and every country figure inherits it.
The Board paper's citation
Determines whether the figure is tested against one construction or three. One footnote saves a week.
Six names, six data items
An item without an owner is an item that arrives late. The date is 11 August and it is back-planned, not arbitrary.
Clearance on the operators
Whether we may approach the two incumbents, and how far the conversation may go given the commercial position.
Entry-mode criteria and weights
Fixed now, printed on the page they decide. Criteria agreed after the scoring are not criteria.
Who attends the interim
Determines whether 8 September is a working session or a rehearsal for the Board. The two need different material.
→ Criteria agreed after the scoring are not criteria — the WP5 weights are set now.
Source: RfP, Verdal Group, 15 July 2026, sections 3-4; mandate VG-STRAT-2026-07.

## Slide 17: Questions